## Product Backlog
Product backlog
ID | Product backlog item | User stories | Priority | Story Points
Customer
1 | Create account | As a customer I would like to be able to create an account so I can log in to my account. | High | 52
2 | Modify shipping address | As a customer I would like to be able to add or modify my shipping address so I can have my correct shipping address stored into my account. | Low | 26
3 | Login | As a customer I would like to be able to log in to my account so I can order products. | High | 52
4 | View products | As a customer I would like to be able to have all products displayed with picture, description, and price so I can make my research. | High | 52
5 | Check out shopping cart | As a customer I would like to check out my products from the shopping cart so I can finalize my order | High | 40
6 | Modify email address | As a customer I would like to be able to modify my email address so I can have my correct email address stored into my account. | low | 26
7 | Delete account | As a customer I would like to be able to delete my account so my personal details are not in risk. |  | 26
8 | Modify shopping cart | As a customer I would like to be able to add or remove products in my shopping cart so I can have a final list of products that I would like to purchase. |  | 40
Company manager
9 | Check customer details | As a company manager, I would like to be able to check all my customer details so I can have an accurate overview of my customers. | low | 26
10 | Check products | As a company manager, I would like to be able to check all my products so I can have an accurate overview of my products. | low | 26
11 | Add new products | As a company manager, I would like to be able to add new products to my online shop so I can offer them for sale to my customers. | High | 52
12 | Manage products | As a company manager, I would like to be able to edit/delete my products so I can have an up-to-date offer of products. | High | 52
13 | appli/remove discount | As a company manager, I would like to be able to apply or remove discount on my products so that I am able to boost my sales. | High | 52
14 | Check order status | As a company manager, I would like to be able to check on the completed an uncompleted order so that I am able to keep track of my deliveries. | Low | 30
Sales manager
15 | View sales data online shop | As a sales manager, I would like to be able to view all my sales data from my online shop so I am able to have an overview on my online sales. | Low | 60
16 | View sales data physical shop | As a sales manager, I would like to be able to view all my sales data from my shops, so I am able to have an overview on my physical sales. | Low | 50
17 | View yearly/monthly sales online | As a sales manager, I would like to have a way of viewing my monthly and yearly sales from my online shop so that I am able to see the sales performance. | Low | 40
18 | View yearly/monthly sales physical | As a sales manager, I would like to have a way of viewing my monthly and yearly sales from my physical shop so that I am able to see the sales performance. | Low | 35
19 | Compare shop productivity | As a sales manager, I would like to have a way of comparing sales from different shops so that I am able to detect my top performant shop. | Low | 25
20 | View top sold products | As a sales manager, I would like to have a way of viewing my top sold products so that I am able to understand which product performs better. | Low | 20
21 | Customer reports | As a sales manager, I would like to have a way of viewing my top customers based on region, age and gender so that I am able to understand how market acts. | Low | 10
22 | Employee performance reports | As a sales manager, I would like to have a way of viewing my top employee sales performance monthly and yearly so that I am able to detect my top performant employee. | Low | 10
23 | Discount campaign reports | As a sales manager, I would like to have a way of viewing the financial efficiency of a discount campaign so that I am able to understand if it has been profitable or not. | Low | 10
24 | View overall business profit | As a sales manager, I would like to have a way of viewing my overall business profitability so that I am able to report further on to my CEO. | Low | 25
Wharehouse manager
25 | Check stock information | As a warehouse manager, I would like to be able to check on my stock information so that I would be able to have an overview over my current stocks | High | 40
26 | Delete products | As a warehouse manager, I would like to be able to add or delete products in my stocks so I can have an accurate list of products in my warehouse. | High | 20
27 | Out of stock notification | As a warehouse manager, I would like to be notified if products are about to go out of stock so I can be able to make orders from suppliers | High | 80

## Burndown chart
Day | Date | Remaining hours |  | Done
|  | Planned | Actual | Done today
0 |  | 768 | 768
1 | 2021-09-01 | 752 | 752 | 16
2 | 2021-09-02 | 736 | 736 | 16
3 | 2021-09-03 | 720 | 720 | 16
4 | 2021-09-06 | 704 | 704 | 16
5 | 2021-09-08 | 688 | 688 | 16
6 | 2021-09-10 | 672 | 672 | 16
7 | 2021-09-13 | 656 | 656 | 16
8 | 2021-09-15 | 640 | 640 | 16
9 | 2021-09-17 | 624 | 624 | 16
10 | 2021-09-20 | 608 | 608 | 16
11 | 2021-09-22 | 592 | 592 | 16
12 | 2021-09-24 | 576 | 576 | 16
13 | 2021-09-27 | 560 | 570 | 6
14 | 2021-09-29 | 544 | 560 | 10
15 | 2021-10-01 | 528 | 550 | 10
16 | 2021-10-04 | 512 | 535 | 15
17 | 2021-10-06 | 496 | 519 | 16
18 | 2021-10-08 | 480 | 499 | 20
19 | 2021-10-11 | 464 | 482 | 17
20 | 2021-10-13 | 448 | 462 | 20
21 | 2021-10-15 | 432 | 440 | 22
22 | 2021-10-18 | 416 | 422 | 18
23 | 2021-10-20 | 400 | 408 | 14
24 | 2021-10-22 | 384 | 392 | 16
25 | 2021-10-25 | 368 | 376 | 16
26 | 2021-10-27 | 352 | 360 | 16
27 | 2021-10-29 | 336 | 344 | 16
28 | 2021-11-01 | 320 | 328 | 16
29 | 2021-11-03 | 304 | 312 | 16
30 | 2021-11-05 | 288 | 296 | 16
31 | 2021-11-08 | 272 | 280 | 16
32 | 2021-11-10 | 256 | 264 | 16
33 | 2021-11-12 | 240 | 248 | 16
34 | 2021-11-15 | 224 | 232 | 16
35 | 2021-11-17 | 208 | 216 | 16
36 | 2021-11-19 | 192 | 200 | 16
37 | 2021-11-22 | 176 | 184 | 16
38 | 2021-11-24 | 160 | 168 | 16
39 | 2021-11-26 | 144 | 152 | 16
40 | 2021-11-29 | 128 | 132 | 20
41 | 2021-12-01 | 112 | 112 | 20
42 | 2021-12-03 | 96 | 98 | 14
43 | 2021-12-06 | 80 | 80 | 18
44 | 2021-12-08 | 64 | 64 | 16
45 | 2021-12-10 | 48 | 48 | 16
46 | 2021-12-13 | 32 | 32 | 16
47 | 2021-12-15 | 16 | 16 | 16
48 | 2021-12-17 | 0 | 0 | 16

## Sprint #1 Backlog
Sprint #1
Id | Product backlog items | User story | Story point | Assigned | Status
1 |  | As a customer I would like to be able to create an account so I can log in to my account. | 52 | Jaume | NOT COMPLETE
2 |  | As a customer I would like to be able to have all products displayed with picture, description, and price so I can make my research. | 52 | Florin | COMPLETE
3
4
5
6
7

## Sprint #2 Backlog
Sprint #2
Id | Product backlog items | User story | Story point | Assigned | Status
1 |  | As a customer I would like to be able to create an account so I can log in to my account. | 52 | Jaume | COMPLETE
2
3 |  | As a company manager I would like to be able to check all my customer details so I can have an accurate overview of my customers. | 26 | Florin | COMPLETE
4 |  | As a company manager I would like to be able to check all my products so I can have an accurate overview of my products. | 26 | Florin | COMPLETE
5
6
7

## Sprint #3 Backlog
Sprint #3
Id | Product backlog items | User story | Story point | Assigned | Status
1 |  | As a customer I would like to be able to log in to my account so I can order products. | 52 | Jaume | COMPLETE
2 |  | As a company manager I would like to be able to add new products to my online shop so I can offer them for sale to my customers. | 52 | Florin | COMPLETE
3
4
5
6
7
8
9
10

## Sprint #4 Backlog
Sprint #4
Id | Product backlog items | User story | Story point | Assigned | Status
1 |  | As a customer I would like to be able to add or modify my shipping address so I can have my correct shipping address stored into my account. | 26 | Jaume | COMPLETE
2 |  | As a company manager I would like to be able to edit/delete my products so I can have an up-to-date offer of products. | 26 | Florin | COMPLETE
3 |  | As a company manager I would like to be able to apply or remove discount on my products so that I am able to boost my sales. | 52 | Florin | COMPLETE

## Sprint #5 Backlog
Sprint #5
Id | Product backlog items | User story | Story point | Assigned | Status
1 |  | As a customer I would like to be able to add or remove products in my shopping cart so I can have a final list of products that I would like to purchase. | 40 | Jaume | COMPLETE
2 |  | As a warehouse manager I would like to be able to check on my stock information so that I would be able to have an overview over my current stocks | 40 | Florin | COMPLETE
3 |  | As a warehouse manager I would like to be notified if products are about to go out of stock so I can be able to make orders from suppliers | 80 | Florin | NOT COMPLETE

## Sprint #6 Backlog
Sprint #6
Id | Product backlog items | User story | Story point | Assigned | Status
1 |  | As a customer I would like to check out my products from the shopping cart so I can finalize my order. | 40 | Jaume | COMPLETE
2 |  | As a warehouse manager I would like to be able to check on my stock information so that I would be able to have an overview over my current stocks | 45 | Florin | COMPLETE
3 |  | As a warehouse manager I would like to be able to add or delete products in my stocks so I can have an accurate list of products in my warehouse. | 20 | Florin | COMPLETE
4
5
6

## Sprint #7 Backlog
Sprint #7
Id | Product backlog items | User story | Story point | Assigned | Status
1 |  | As a customer I would like to be able to modify my email address so I can have my correct email address stored into my account. | 26 | Jaume | COMPLETE
2 |  | As a customer I would like to be able to delete my account so my personal details are not in risk. | 26 | Jaume | COMPLETE
3 |  | As a warehouse manager I would like to be notified if products are about to go out of stock so I can be able to make orders from suppliers | 52 | Florin | COMPLETE
4
5
6

## Sprint #8 Backlog
Sprint #7
Id | Product backlog items | User story | Story point | Assigned | Status
1 |  | Process Report | 40 | All | Completed
2 |  | Project Report | 64 | All | Completed
3
4
5
6